Smithycroft Secondary School - Improvement Planning 2025-26

| School | Smithycroft Secondary School |
| --- | --- |
| Learning Community | Smithycroft |
| Link Officer | Samir Sharma |
| Head of Service | Jean Miller |
| School Roll | 933 (2024-25) |
| Attendance Rate | 86.1% |
| Pupils affected by the poverty related attainment gap (employment, income, housing, health, access to services, education, crime), covid & other forms of poverty not listed OTHER – Pupils not in SIMD 1 & 2, not in receipt of school meals but affected by factors detailed above. |  |
| PEF allocation 25-26: £188,000; SIMD Quintile 1 (% and Number) – 62% - 510. PEF Carry Forward: £56,000; SIMD Quintile 5 (% and Number) – 1.4% - 13. Total PEF Allocation 25-26: £244,000. FME (number and %); Total No Pupils - 944. |
| Grand Challenges 2023-26 (Grand Challenges are the long term strategic changes you intend to achieve i.e. ‘to improve attainment in literacy’) - Improving young people’s experience of learning in class - Improving attainment for all young people |  |

| Grand Challenge: Improving young people’s experience of learning in class |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mission: To implement the Smithycroft Lesson Cycle to ensure a consistently ‘Very Good’ experience for young people |  |  |  | QI (HGIOS 4) 2.3 – Learning, Teaching and Assessment |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility |  | Target Date | Core | PEF |
| Agree outline structure of lesson cycle | All staff are aware of and understand the lesson cycle and the rationale for implementation | Views – Staff report an awareness and understanding of the lesson cycle and its rationale. | LM |  | August 2025 |  |  |
| Identify and exemplify the key features of the ‘Connect’ phase’ | Almost all young people experience the same ‘connect’ phase in every lesson, every day. | Observations – of learning demonstrate young people consistently experiencing a ‘Connect’ phase with the same key features. Views – young people report the above consistent experience. | LM |  | October 2025 |  |  |
| Develop collegiate calendar to support implementation of lesson cycle | All staff are supported in delivering a consistent experience for young people | Data - Collegiate Calendar established Views – Staff report collegiate time as supporting the delivery of a consistent experience for young people | PO/LM |  | August 2025 October 2025 |  |  |
| Develop strategies to ensure that young people are involved in approaches to improving learning | Almost all young people are involved in school improvement around learning. | Views – young people report being involved in strategies to improve their learning. | DB |  | October 2025 |  |  |
| Explore further ways to embed the five key elements in the cycle | Almost all staff use specific identified pedagogy to improve learning | Observations – of learning demonstrate that specific pedagogies are in consistent use Data – Updated L and T strategy identifying such strategies | LM |  | December 2025 May 2026 |  |  |
| Review initial stage of lesson structure implementation | Almost all staff and young people are involved in planning next steps of the L and T strategy. | Views – Staff and young people report positively that they are involved in the next steps to improve learning | LM |  | October 2025 |  |  |
| Dec/May Evaluative Comments on impact of SIP work: (Used to support completion of SER) |  |  |  |  |  |  |  |

| Grand Challenge: Improving young people’s experience of learning in class |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mission: To develop a new curriculum rationale and curriculum map to meet all learners needs |  |  |  | QI (HGIOS 4) 1.3 Leadership of Change |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility |  | Target Date | Core | PEF |
| Form a small Improvement Team | Members, led by APH, will work collaboratively towards achieving our Mission | Observations – an improvement team of enthusiastic and committed individuals is created | APH |  | August 2025 |  |  |
| Research current examples of curriculum rationales | Professional reading and visits to other schools will allow us to create a curriculum rationale which best suits Smithycroft’ s context | Views – improvement team report feeling fully informed and confident about starting to create a new curriculum rationale best suited to Smithycroft’ s context | APH |  | September 2025 |  |  |
| New curriculum rationale created | A new curriculum rationale is created through consideration of robust evidence gathered through the team’s research | Observations – of a curriculum rationale allowing us to create a curriculum which will meet the needs of all learners, allowing students to embark on engaging and challenging learning pathways best suited to their interests and abilities. Views – all stakeholders report the above | APH |  | October 2025 |  |  |
| Proposed curriculum map for 26/27 created | A curriculum map for the 26/27 session is created which offers a better learning and achievement experience for all learners | Observations – of a curriculum map allowing students to embark on engaging and challenging learning pathways best suited to their interests and abilities whilst also meeting the needs of students who have already embarked on their SQA Senior Phase journey | APH |  | December 2025 |  |  |
| Dec/May Evaluative Comments on impact of SIP work: (Used to support completion of SER) |  |  |  |  |  |  |  |

| Grand Challenge: Improving young people’s experience of learning in class |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mission: To embed the school’s new vision and values in every area, every day. |  |  |  | QI (HGIOS 4) 1.3 Leadership of Change |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility |  | Target Date | Core | PEF |
| Agree one sentence definition of each value | All stakeholders are aware of the definitions and have a visual prompt to support | Views - staff report clarity around understanding the shared meaning of the values | RL |  | August 2025 |  |  |
| Creation of staff working group | Team work collaboratively to fulfil the commitments outlined | Observations – working group work to create ‘scripts’ to support staff in using the agreed language around values Views- staff report clarity and enhanced understanding of how to talk about the values with young people in a consistent way | RL |  | September 2025 October 2025 |  |  |
| Delivery of Year group Assembly with different value as the focus | All young people will be aware of new vision and values and begin to develop a deeper understanding of what they mean and why they are important to our school | Views – young people will be able to articulate the values and understand why they are important Data – data collected following each assembly will provide a baseline starting point of understanding of values, which can be compared to data later in the year to measure impact | RL |  | August 2025 – September 2025 |  |  |
| Extensive consultation with staff and young people to co-create examples of how the Vision and | Creation of a more detailed document that exemplifies the Vision and Values to ensure that all stakeholders are aware of | Data – Creation of a comprehensive list of daily actions that reflect the vision and values Observations - staff and young people will have a clear understanding of how to exemplify the Vision and Values and we will see strong evidence of this | RL |  | October 2025 – December 2025 |  |  |
| Values can be lived out on a daily basis | how to maximise their actions to reflect the Vision and Values | Observations - staff and young people will have a clear understanding of how to exemplify the Vision and Values and we will see strong evidence of this | RL |  |  |  |  |
| Creation of visual representations of the school values and vision and development of strategy on how we recognise and reward | Development of graphics in conjunction with all stakeholders to create a visual depiction of our vision and values Clear and consistent strategy on how we acknowledge and ‘reward’ young people when we see them demonstrating our school values | Observations: stakeholders report positively about the visual representations and will use them regularly to support use of values | RL |  | Jan 2026 |  |  |
| Raising the visibility and profile of Vision and Values across the school community | Production of a range of ‘graphics’ around school to promote visibility and status of vision and values around school | Data: data gathered to record actions will show that they are being widely used across the school community | RL |  | April 2026 |  |  |
| The Vision and Values are embedded into everyday actions across the school community | All stakeholders live out the school’s vision and values daily. All stakeholders have ownership over the school’s vision and values and can articulate how they demonstrate them. Vision and Values are embedded in curriculum planning, whole school policies, assemblies and classroom practice All behaviour around the school community is aligned with the vision and values. | Views: All stakeholders report confidence using the new values to support all aspects of school life Observation: Vision and Values are embedded in curriculum planning, whole school policies, assemblies and classroom practice. These practices should be highly visible and recognisable Data: Carry out same surveys from earlier on in year to measure the impact of strategic work throughout the year. Data should show an increase in understanding. | RL |  | May 2026 |  |  |

| Grand Challenge: Improving attainment for all young people |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mission: To raise expectations for all using a data-led approach |  |  |  | QI (HGIOS 4) 3.2 Raising Attainment and Achievement |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility |  | Target Date | Core | PEF |
| Establish and track subject by subject attainment baselines in the Senior Phase. | Almost all young people are aspirationally presented at SQA levels that reflect a national comparison | Data – Presentation levels for SQA courses demonstrate an increase on 2024-25 Data - % of young people attaining full course awards at level 4, 5 and 6 is in line with VC | JS/PO |  | August 2025 At each tracking period thereafter |  |  |
| Develop and evaluate a streamlined approach to working with key data including CAT baselines | All staff are aware of and understand whole school approaches to key data, leading to greater level of challenge for young people | Views – Almost all staff report an enhanced awareness of key whole school data | JS/PO |  | October 2025 |  |  |
| Devise and implement a revised approach to level setting and intervention | Almost all young people are aspirationally presented at SQA levels that reflect a national comparison | Data – Presentation levels for SQA courses demonstrate an increase on 2024-25 Data - % of young people attaining full course awards at level 4, 5 and 6 is in line with VC | JS |  | August 2025 At each tracking period thereafter |  |  |
| Further embed the whole school Self-Evaluation calendar | All staff show an understanding of key whole school process around self-evaluation, leading to improvements in learning and attainment | Views – Staff report an increased understanding of key evaluation processes Data - % of young people attaining full course awards at level 4, 5 and 6 is in line with VC | JS |  | October 2025 At tracking periods |  |  |
| Dec/May Evaluative Comments on impact of SIP work: (Used to support completion of SER) |  |  |  |  |  |  |  |

| Grand Challenge: Improving attainment for all young people |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mission to embed a greater level of challenge in the Broad General Education: |  |  |  | QI (HGIOS 4) 3.2 Raising Attainment and Achievement |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility |  | Target Date | Core | PEF |
| Review approaches to curricula planning in the BGE using 4th level benchmarks. | Almost all young people benefit from an increased level of challenge in almost all classrooms | Views – young people report that learning is more challenging in general across the school Data – all curricular plans have level 4 benchmarks embedded across the BGE | RL/SB |  | December 2025 |  |  |
| Review approaches to tracking and assessment in the BGE | Almost all young people have a clearer idea of the progress they are making in their learning | Views – Young people report knowing their next steps in learning Data – Tracking and Monitoring policy established that recognises new whole school approach. | RL/SB RL |  | December 2025 October 2025 |  |  |
| Devise and implement consistent approaches to targeted intervention in the Broad General Education | Identified young people in S1 -S3 benefit from clear targeted approaches to improving their attainment. | Data – comparisons between tracking reports about progress in targeted areas demonstrate improved attainment Views – young people report positively about their involvement in targeted intervention and the impact on their learning. | JS/RL |  | January and February 2026 December 2025 |  |  |
| Dec/May Evaluative Comments on impact of SIP work: (Used to support completion of SER) |  |  |  |  |  |  |  |

| Grand Challenge | Area of Focus | QI HGIOS 4 |
| --- | --- | --- |
| Early intervention and prevention | Attendance | 3.1 Inclusion and Wellbeing |
| Early intervention and prevention | Staged Intervention | 3.1 Inclusion and Wellbeing |
| Early intervention and prevention | Nurture | 3.1 Inclusion and Wellbeing |
| Dec/May Evaluative Comments on impact of maintenance agenda work : (Used to support completion of SER) |  |  |

Maintenance Agenda:

Please use the space below to note any other improvement actions initiated in previous years which are continuing to be a focus in the coming year but not on your identified priorities for 25-26

PPl